Software Engineering & Project Management (BCS501) - Module 3

PART 1: AGILE DEVELOPMENT

1. What is "Agility"?

Imagine building a house, but the owner keeps changing their mind about where the kitchen should be. In traditional construction, this is a disaster. In software, this happens all the time.

Agility is a mindset and methodology designed to handle change.

- Definition: Building software in short chunks (iterations of 1-4 weeks) so you can adapt quickly if business needs change.

- The Goal: Deliver a working model to the customer quickly.

- Key Concept: Change is not the enemy; it is inevitable. An agile team is "nimble"—it expects change and responds to it rather than fighting it.

Agility and the "Cost of Change"

- Traditional View: Changing a requirement late in the project (e.g., right before launch) costs a fortune because you have to undo months of work.

- Agile View: Because you release software in small increments, you catch changes early. This "flattens" the cost curve, meaning a late change doesn't cost significantly more than an early one.

2. What is an Agile Process?

An Agile process is based on three truths about software:

- Unpredictability: You can't predict all requirements in advance.

- Interleaving: Design and building (coding) happen at the same time, not separately.

- Adaptability: Analysis, design, and testing are not predictable steps.

How to handle this?

- Incremental Adaptation: Don't try to build the whole thing at once. Build a little, get feedback, adjust, and build a little more.

- Customer Feedback: Show the customer a working prototype frequently to ensure you are on the right track.

The 12 Agile Principles (Simplified)

- Satisfy the customer via early delivery.

- Welcome change, even late in the project.

- Deliver frequently (weeks, not months).

- Work together: Developers and business people must talk daily.

- Trust the team: Give motivated people the environment they need.

- Face-to-face conversation is best.

- Working software is the only real measure of progress.

- Sustainable pace: Don't burn out; keep a steady speed.

- Technical excellence makes you more agile.

- Simplicity: The art of not doing work that isn't needed.

- Self-organizing teams make the best designs.

- Reflect and tune: Regularly check how to become more effective.

Human Factors

Agile relies on people, not just tools. A good agile team needs:

- Competence: Skill and knowledge.

- Common Focus: Everyone aims for the same goal (delivery).

- Collaboration: Working together, not in silos.

- Decision-making ability: The team has the freedom to control its own work.

- Mutual Trust: Treating each other with respect.

- Self-Organization: The team decides how to organize the work and the schedule.

3. Extreme Programming (XP)

XP is the most famous Agile method. It takes good practices and turns the dial up to "extreme."

XP Values

- Communication: Constant talk between team and customer.

- Simplicity: Design only for immediate needs, not future possibilities.

- Feedback: Test constantly.

- Courage (Discipline): Be brave enough to throw away code if it's wrong or to design for today knowing it might change tomorrow.

- Respect: For team members and the software.

The XP Process Loop

- Planning:

  - User Stories: The customer writes requirements on index cards (e.g., "As a user, I want to login").

  - Value & Cost: Customer sets priority (value); Developers set cost (time to build).

- Design:

  - KIS Principle: Keep It Simple.

  - Spike Solutions: Creating a quick prototype to solve a tough problem.

  - Refactoring: Cleaning up the code to make it efficient without changing what it does.

- Coding:

  - Unit Tests First: Write the test before you write the code.

  - Pair Programming: Two people work at one computer. One types, the other thinks/reviews. This catches errors instantly.

- Testing:

  - Continuous Integration: New code is tested and combined with the main software daily.

  - Acceptance Tests: Tests specified by the customer to ensure the features work as requested.

Industrial XP (IXP)

XP adapted for large organizations. It adds:

- Readiness Assessment: Is the company ready for Agile?

- Project Community: Involving not just devs, but legal, sales, quality, etc.

- Retrospectives: Reviewing the process after delivery to learn lessons.

4. Other Agile Process Models

Adaptive Software Development (ASD)

Focused on complex systems.

- Cycle: Speculation (Planning) -> Collaboration (Building) -> Learning (Reviewing).

- Philosophy: Focus on human collaboration and self-organization.

Scrum

Very popular framework for managing work.

- Backlog: A prioritized list of everything that needs to be done.

- Sprints: Short time-boxes (e.g., 30 days) where a specific set of backlog items are built. No changes are allowed during a sprint.

- Scrum Meetings: 15-minute daily stand-up meeting.

  - What did you do yesterday?

  - What will you do today?

  - Are there any obstacles?

- Demo: Showing the working software at the end of a sprint.

Dynamic Systems Development Method (DSDM)

- Pareto Principle (80/20 Rule): 80% of the application can be delivered in 20% of the time.

- Focus: Deliver "enough" to move to the next step. Don't aim for perfection immediately.

Feature Driven Development (FDD)

- Feature: A small client-valued function (e.g., "Calculate total sale").

- Process: Develop an overall model -> Build a feature list -> Plan by feature -> Design by feature -> Build by feature.

Lean Software Development (LSD)

Adapted from lean manufacturing (like Toyota).

- Core Principles: Eliminate waste (useless features), build quality in, defer commitment (decide as late as possible), deliver fast.

Agile Modeling (AM)

- Philosophy: Models (diagrams/docs) should be "barely good enough."

- Travel Light: Don't keep models you don't need. Content is more important than making the diagram look pretty.

PART 2: PRINCIPLES THAT GUIDE PRACTICE

This section moves away from "Agile" specifically and talks about general rules (Principles) that good software engineers follow, regardless of the method.

1. Core Principles

Principles guiding the PROCESS (The "How"):

- Be Agile: Keep it simple, keep it concise.

- Focus on Quality: Never cut corners on quality.

- Be Ready to Adapt: Adjust to the project conditions.

- Build an Effective Team: Trust and respect are key.

- Communication: Coordinate effectively.

- Manage Change: Have a plan for how to handle updates.

- Assess Risk: What could go wrong?

- Provide Value: Don't produce useless documents.

Principles guiding the PRACTICE (The "Technical Work"):

- Divide and Conquer: Break big problems into small pieces.

- Abstraction: Use simple terms to describe complex things.

- Consistency: Use the same style for coding, designing, and documenting.

- Information Transfer: Focus on how data moves from one place to another.

- Modularity: Build software in distinct blocks (modules).

- Patterns: Look for recurring problems and use established solutions.

- Multiple Perspectives: Look at a problem from different angles.

- Maintenance: Remember that someone else will have to fix your code later.

2. Principles for Each Activity

A. Communication Principles (Talking to the Customer)

- Listen: Don't just plan your response.

- Prepare: Understand the problem before the meeting.

- Facilitator: Someone must lead the meeting.

- Face-to-face: Better than email, but bring drawings/docs.

- Take Notes: Document decisions.

- Collaborate: Work together to find consensus.

- Modularize: Stick to one topic at a time.

- Draw Pictures: If words fail, sketch it out.

- Move On: If you agree (or can't agree), move to the next point. Don't loop endlessly.

B. Planning Principles (The Roadmap)

- Understand Scope: Know what you are building.

- Involve Stakeholders: Developers and customers plan together.

- Iterative: The plan will change.

- Estimate: Based on what you know (even if vague).

- Consider Risk: Have a Plan B.

- Be Realistic: People don't work 100% of the time; mistakes happen.

- Granularity: Plan near-term tasks in detail, long-term tasks loosely.

- Quality Assurance: Plan how you will test.

- Accommodate Change: Define how changes will be handled.

C. Modeling Principles (Diagramming/Designing)

- Goal: The goal is to build software, not to create diagrams.

- Travel Light: Only create models you actually need.

- Simplicity: A simple model leads to simple software.

- Change: Expect the models to change.

- Purpose: Know why you are drawing this diagram.

- Feedback: Get reviews on your models early.

Requirements Modeling: Focus on the "What" (What data comes in? What functions are needed? How does the system behave?). Design Modeling: Focus on the "How" (Architecture, Data structures, Interfaces). Traceability is key—every design element should trace back to a requirement.

D. Construction Principles (Coding & Testing)

Coding:

- Preparation: Understand the problem and design before typing code.

- Practice: Use structured programming, meaningful variable names, and self-documenting code.

- Refactoring: Continuously improve the code structure.

Testing:

- Traceability: Tests must check if requirements are met.

- Plan Ahead: Plan tests before you write code.

- Pareto Principle: 80% of errors are usually in 20% of the code. Find that 20%.

- Small to Large: Test individual units first, then the whole system.

- Exhaustive testing is impossible: You can't test every single path, so test the logic intelligently.

E. Deployment Principles (Delivery)

- Manage Expectations: Don't promise more than you can deliver.

- Complete Package: Deliver the software + support data + documentation together.

- Support Regime: Have a plan for tech support before you launch.

- Instruction: Provide manuals or training.

- Buggy Software: Do not deliver known bugs with a promise to "fix it later." It destroys trust.

Software Engineering & Project Management (BCS501) - Module 4

PART 1: INTRODUCTION TO PROJECT MANAGEMENT

1. What is Software Project Management (SPM)?

Software Project Management is the art and science of planning and leading software projects from a mere idea into a finished reality. It involves managing four key elements (The 4 P's):

- People: The team building the software.

- Product: The software itself.

- Process: The set of steps used to build it.

- Project: The overall work and timeline.

Why do we need management? Because software is complex and takes a long time to build. Without a plan, you might deliver a product that is too expensive, late, or doesn't work.

2. The "Triple Constraint" (Project Triangle)

Every project is a balancing act between three main forces. You usually can't change one without affecting the others.

- Time: How long do we have?

- Cost: What is the budget? (Resources, Money)

- Quality: How good must the final result be?

Note: Sometimes "Scope" is added as a fourth dimension. If you want high quality and low cost, it will take a lot of Time. If you want it fast and cheap, Quality will suffer.

3. Why do Software Projects Fail?

Statistics show a grim picture (e.g., the Standish Group report).

- Only about 1/3 of projects are fully successful.

- Many are late (82%) or over budget (43%).

- Reasons for failure: Poor management, uncontrolled changes ("scope creep"), and lack of clear requirements.

PART 2: THE NATURE OF PROJECTS

1. What distinguishes a "Project" from a "Job"?

A Job is a routine, repetitive task (e.g., manufacturing the same car part every day). A Project is a unique undertaking with a specific goal.

Characteristics of a Project:

- Non-routine: You are doing something new.

- Planned: It requires a schedule.

- Specific Objectives: It has a clear goal (e.g., "Build a Payroll System").

- Time-Span: It has a definite start and end date.

2. Software Projects vs. Other Projects (e.g., Construction)

Managing a software project is harder than building a bridge because of four special characteristics:

- Invisibility: You can't "see" progress on software like you can see a bridge rising. You rely on reports.

- Complexity: Software has more moving parts and logic paths than most physical structures.

- Conformity: Physical engineers follow laws of physics (consistent). Software engineers must conform to human clients (inconsistent).

- Flexibility: People think software is easy to change ("It's just code!"). This leads to constant changes requests, which destabilizes the project.

PART 3: MANAGEMENT ACTIVITIES & LIFECYCLE

1. The Management Cycle

Management isn't just giving orders. It follows a cycle:

- Feasibility Study: Is this project worth doing? (Financial & Technical check).

- Planning: How do we do it? (Creating the roadmap).

- Execution: Do it! (Building the software).

During execution, the manager performs the Control Cycle:

- Data Collection: Gather info on progress (e.g., "We wrote 500 lines of code").

- Data Processing: Convert to useful info (e.g., "We are 2 days behind schedule").

- Decision Making: Take corrective action (e.g., "Add one more developer").

2. Plans vs. Methods vs. Methodologies

- Method: A technical way of doing something (e.g., "We will use unit testing").

- Plan: Applying the method to a specific timeline (e.g., "John will do unit testing on Monday").

- Methodology: A group of methods used together (e.g., Agile, Waterfall).

3. Stakeholders

Stakeholders are people who care about the project. They fall into three groups:

- Internal to the team: The developers, project manager.

- External to the team (but inside the company): Senior management, other departments (e.g., database admins).

- External to the company: The client (customer), users, suppliers/contractors.

Theory W (Win-Win): A good manager tries to make sure all stakeholders get something beneficial from the project.

4. Setting Objectives (SMART)

Don't just say "We want better software." Use SMART goals:

- Specific: Concrete and well-defined.

- Measurable: Can you measure success? (e.g., "Reduce errors by 10%").

- Achievable: Is it possible?

- Relevant: Does it help the business?

- Time-constrained: Is there a deadline?

PART 4: PROJECT EVALUATION (Is it worth it?)

Before starting, you must evaluate if a project makes financial sense. This is called the Business Case.

1. Cost-Benefit Analysis

You compare the Costs (Development staff, Hardware, Setup) against the Benefits (money saved, new revenue).

- Net Profit: Total Income - Total Cost.

  - Flaw: It doesn't care when you get the money. £50k profit in year 1 is better than £50k profit in year 10, but "Net Profit" treats them the same.

2. Payback Period

How long until the project pays for itself?

- Example: You spend £100,000. The project earns £20,000 per year.

- Payback Period: 5 years.

- Goal: Shorter is better.

3. Return on Investment (ROI)

A percentage that tells you how efficient the investment is.

$$\text{ROI} = \frac{\text{Average Annual Profit}}{\text{Total Investment}} \times 100$$

- Example: Investment £100,000. Net profit £50,000 over 5 years (avg £10,000/year).

- ROI = (10,000 / 100,000) * 100 = 10%.

4. Net Present Value (NPV) - The Best Method

Money today is worth more than money tomorrow (due to inflation and interest rates). NPV discounts future cash flows to what they are worth today.

- Discount Rate: The interest rate you could have earned if you left the money in the bank (e.g., 10%).

- If NPV is Positive: The project is a good investment.

- If NPV is Negative: You would make more money just putting the cash in a bank.

5. Risk Evaluation

Projects have risks. We must identify and rank them.

- Risk Matrix: A table listing risks by Importance (High/Medium/Low) and Likelihood (High/Medium/Low).

- Decision Trees: A diagram used to make decisions when outcomes are uncertain. You calculate the "Expected Value" of each path (Value × Probability).

PART 5: MODERN VS. TRADITIONAL MANAGEMENT

| Traditional Management | Modern Management |
| --- | --- |
| Planning: Detailed plan made upfront. | Planning: Incremental planning (plan as you go). |
| Quality: Checked at the end. | Quality: Checked constantly. |
| Change: Avoided (frozen requirements). | Change: Welcomed and managed. |
| Release: One big release at the end. | Release: Frequent, small releases. |

Software Engineering & Project Management (BCS501) - Module 5

PART 1: SOFTWARE QUALITY

1. What is Software Quality?

"Quality" is a vague word. Everyone agrees it is "a good thing," but what does it actually mean in software?

- Traditional Definition: Fitness for purpose. Does the software do what the user asked for (SRS document)?

- Modern View: It's not just about features; it's about specific attributes like reliability, speed, and ease of use.

Crucial Concept: You cannot wait until the end to measure quality. If you find out the software is bad the day before delivery, it is too late. You must define quality goals during planning.

Why is Quality Important?

- Criticality: Software runs aircraft, hospitals, and banks. Failures can be dangerous or expensive.

- Cost of Errors: Fixing a bug early (during design) is cheap. Fixing it after release is enormously expensive.

- Intangibility: You can't "see" software rot. You need metrics to know if it's good.

2. Defining Quality (The "ilities")

To measure quality, we break it down into specific characteristics. These are often grouped into three categories (McCall’s Model):

A. Product Operation (Using it day-to-day)

- Correctness: Does it do what the spec says?

- Reliability: Does it work without crashing?

- Efficiency: Does it run fast and use low memory?

- Integrity: Is it secure from hackers?

- Usability: Is it easy to learn and use?

B. Product Revision (Changing it later)

- Maintainability: How easy is it to find and fix a bug?

- Testability: How easy is it to test?

- Flexibility: Can we add new features easily?

C. Product Transition (Moving it elsewhere)

- Portability: Can I move it from Windows to Linux?

- Reusability: Can I use parts of this code in a new project?

- Interoperability: Can it talk to other systems?

3. Software Quality Models

Different experts have different ways of organizing these quality attributes.

1. McCall’s Model

(Described above: Operation, Revision, Transition).

2. Boehm’s Model

Focuses on "Utility" (how useful is it?).

- High-level traits: As-is Utility, Maintainability, Portability.

3. Dromey’s Model

Links high-level properties (like "Correctness") to specific software attributes (like "Variable naming conventions"). It connects the concept of quality to the code itself.

4. ISO 9126 ( The Industry Standard)

This is the most important one. It defines 6 major characteristics:

- Functionality: Does it satisfy user needs? (Security, Accuracy).

- Reliability: Can it maintain performance? (Fault tolerance, Recoverability).

- Usability: Effort needed to use it. (Understandability, Learnability).

- Efficiency: Resource usage vs. performance. (Time behavior).

- Maintainability: Effort to change it. (Analyzability, Stability).

- Portability: Ability to transfer to another environment. (Installability).

4. Metrics: Measuring Quality

You can't improve what you don't measure. We use two types of metrics:

| Product Metrics | Process Metrics |
| --- | --- |
| Measure the software itself. | Measure the method used to build it. |
| Examples: Lines of Code (LOC), Response time (seconds), Number of defects found. | Examples: Average time to fix a bug, Effectiveness of code reviews. |
| Goal: Assess the final deliverable. | Goal: Improve the way the team works. |

PART 2: SOFTWARE PROJECT ESTIMATION

1. Why Estimate?

Estimation is predicting the future: How much effort, time, and money will this project take?

- Uncertainty: Estimates are never 100% accurate.

- Cone of Uncertainty: Estimates get better as the project progresses.

- The Golden Rule: Never rely on just one estimation method. Use at least two and compare them.

2. The Planning Process

Planning is not a one-time event. It involves:

- Scope: What exactly are we building? (Narratives or Use Cases).

- Feasibility: Can we actually build it? (Technology, Finance, Time).

- Resources: What/Who do we need?

  - People: Skills and location.

  - Reusable Software: Don't reinvent the wheel. Use Off-the-shelf (COTS) or existing components.

  - Environment: Hardware and tools (SEE - Software Engineering Environment).

3. Estimation Techniques

How do we actually come up with a number?

A. Decomposition Techniques (Divide and Conquer)

Break the big problem into small, manageable pieces.

- LOC-Based (Lines of Code):

  - Break system into functions.

  - Guess the lines of code for each function.

  - Use history to know "Cost per Line of Code".

  - Problem: Different languages take different amounts of lines to do the same thing.

- FP-Based (Function Points):

  - Count the "things" the software deals with: Inputs, Outputs, Inquiries, Files, Interfaces.

  - Apply a "complexity weight" (Simple/Medium/Complex).

  - Result is a number (Function Points) independent of programming language.

- Process-Based:

  - Don't list software functions. List tasks (e.g., "Design Interface", "Test Database").

  - Estimate effort for each task.

B. Use-Case Based Estimation

- Use cases describe user interactions.

- Challenge: One use case might be 5 lines of code; another might be 5,000.

- Solution: You must determine the "level" and "complexity" of the use case (e.g., number of scenarios or pages) to estimate its size.

C. Empirical Models (The Formulas)

Using formulas derived from historical data of thousands of projects.

- General Formula: $Effort = A + B \times (Size)^C$

- COCOMO II (Constructive Cost Model): Created by Barry Boehm. It has three stages:

  - Application Composition: Early stage, uses Object Points (Screens/Reports).

  - Early Design: Uses Function Points.

  - Post-Architecture: Detailed stage, uses Lines of Code.

- The Software Equation: A dynamic model that relates Effort, Project Duration (Time), and Size. It shows that extending the deadline slightly can drastically reduce the effort required (and vice versa).

4. Reconciling Estimates

You calculated effort using LOC and got 46 person-months. You calculated effort using Use-Cases and got 68 person-months.

- What now? Do not just average them.

- Investigate: Why are they different? Did the LOC estimate miss a feature? Did the Use-Case estimate assume the team was inexperienced?

- Converge: Adjust assumptions until the estimates are close.

PART 3: MODERN VS TRADITIONAL ESTIMATION

| Traditional | Modern (Agile/Extreme) |
| --- | --- |
| Plan everything in detail upfront. | Plan incrementally (just enough for the next step). |
| Focus on exact size (LOC). | Focus on "Fuzzy Logic" or T-shirt sizing (S, M, L). |
| Updates are rare. | Updates happen constantly as more is learned. |